## 2017_GAD Accomplishment
ANNUAL GENDER AND DEVELOPMENT (GAD) ACCOMPLISHMENT REPORT
FY 2017
Region VI | [5 empty] | Total LGU Budget : |  |  |  |  | 64093030
Province of Iloilo | [5 empty] | Total GAD Budget : |  |  |  |  | 3615000
Municipality of Bingawan
Gender Issue or GAD Mandate | GAD Objective | Relevant LGU Program or Project | GAD Activity | Performance Indicator and Target | Actual Results | Approved GAD Budget | Approved GAD Budget (6) |  |  | Actual Cost or GAD Expenditure | Variance or Remarks
[7 empty] | MOOE | PS | CO
(1) | (2) | (3) | (4) | (5) | (6) | (7) |  |  |  | (8) | (9)
CLIENT FOCUSED
61% of female population ages 15-64 are unemployed | To increase livelihood opportunities for women by 6% at the end of 2017 | 1. Livelihood Program a. Food Processing b. Vegetable seed dispersal c. Vegetable processing | 1. Organize women's group 2. Orientation on Gender and Women's Economic Empowerment 3. Skills Enhancement | 1. additional 2 women's group organized 2. Conducted orientation on Gender and Women's economic empowerment to 3 women's organization 3. Conducted skills enhancement training to 3 women's organization. | 1. 5 women's group organized (Malitbog Ilaya Women's Association, Bulabog Women's Association, Poblacion SLP Association, Jesus Saves Baptist Church RIC, Malitbog Ilaya RIC), and Reorganized Ngingi-an SLP Association. 2. One Gender And Development advocacy conducted at Jovita Alfaras Rivera National High School 3.Training on Soap Making conducted (30pax) 4. Training on Swine fattening conducted (32pax) 5. Training on Coffee production conducted (30pax) | 50000 | 20000 |  |  | 20000 | 30,000 Other program funded by PCDO/ ITLDC (20,000.00) DA RFO6 (475,000.00)
More than 50% household have no access to safe drinking water | To increase access to safe drinking water by 10% at the end of 2017 | Water Management System Program | 1. Conduct water sampling and regular chlorination of water sources 2. Provision of jetmatic pump with culvert pipe | 1. Chlorinated to 70 water sources every month 2. Provided 5 units of jetmatic pump per barangays | > 200 water sources were chlorinated in 2017 > Purchased 5 jetmatic pump > Construction of rainwater catchment | 250000 | 137989 |  | 87250 | 225239 | 24,761.00 Other program funded by Provincial Health Office
Absence of Gender-Responsive public facilities | To provide Gender-responsive facilities | Provision of gender responsive facilities | 1. Establishment/Improvement of Gender-Responsive Public Toilets | 1. atleast 1 gender-responsive public toilet | Maintained public facilities | 100000 | 54750 |  |  | 54750 | 45,250.00 To be implemented in 2018
22% Contraceptive Prevalence Rate (CPR) | To increase CPR by 65% | Family Planning Program | 1. Conduct FPAs for SPAs/NHTS couples 2. Purchase of FP commodities | 1. Conduct twice a month FPAs for SPAs/NHTS couples 2. Purchase and distributed of FP commodities to ______ beneficiaries | > USAPAN Sessions were conducted to 470 woman | 100000 | 48700 |  |  | 48700 | Other program funded by Provincial Health Office
19% of household have no access to sanitary toilets | To increased by 85% HH has access sanitary toilets | Waste disposal management program | Provision of sanitary toilet through counterparting NHTS/PHO and LGU | Provided complete materials (cement, toilet bowls, Pipes) to 200 beneficiaries | > 10 toilet bowls and 30 cements were distributed to beneficiaries in Brgy. Quinangyana >20 drums for sanitary septic tanks were given to beneficiaries in Brgy. Alabidhan | 300000 |  |  | 76000 | 76000 | 224,000.00 funded by Provincial Health Office
Residents are not secured at night because 50% of municipal streets lights are not functional | to provide secured environment and sustain the 0% street crime in the municipality | repair and maintenance of streetlights | repair of non-functional municipal streetlights in Brgy. Poblacion | 70% of the municipal street lights are functional | > 3 street lights installed in Brgy. Cairohan, Bulabog, and Castroverde Street > Repair of municipal street lights | 100000 |  |  | 228514 | 228514 | 128,514.00 Urgent need to install additional street lights
High incidence of PWDs with Mental Retardation | To decrease incidence of PWD with MR | PWD Program | 1. Organize PWDs 2. Profiling of MRs 3. Distribution of IEC Materials | 1. atleast 1 PWD group organized 2. Collected data of PWD 3.Distributed IEC Materials | > 1 PWD Group organized (brgy Quinangyana) > Registered 85 PWD and registered online | 30000 | 30000 |  |  | 30000
11 barangays have inactive women's organization | To reactivate/reorganize women's organization | Strengtheing of Women's Organization | 1. Capability training and skills training 2. Conduct meetings | 1. Capability training and skills training 2. Conduct meetings | 2 women groups were organized | 30000 | 30000 |  |  | 30000
14 barangays have Inactive OSY program | To activate OSY organization(PYAP) | Youth Development Program | 1. Sports Activities 2. Encampment 3. Peer helpers training | 1. conducted sports activities, encampment , and peer helpers training | > Representation of 1 youth leader in Provincial Youth Organization > Special Program for the Employment of Students | 20000 | 136000 |  |  | 136000 | 116,000.00 Local Counterpart for SPES Program
Not complete learning materials in the teen-center | To provide additional learning materials for the teen-centers |  | Acquisition of learning materials for teen-center | Acquired learning materials and equipments for teen center | > Acquired musical instruments, laptop, and other equipment for Bingawan NHS Teen Center | 100000 |  |  | 100000 | 100000
Lack of awareness on Senior Citizen privileges | To increase awareness of SC on their priviledges and responsibilities | SC Program and Services | 1. IEC 2. General Assembly 3. Symposium | Conducted general assembly and symposium for SC | > conducted 12 monthly meeting > conducted general assembly | 100000 | 100000 |  |  | 100000
No shelter for victims of CICL, abused women and child | To provide shelter for victims of CICL abused women and children | Rehabilitation and Intervention Program for CICL, Victims of Violence | Construction of Crisis Center | Constructed Crisis Center for Children and Victim of Violence | > 1 MOA with Balay Paglaom in Mina, Iloilo | 500000 |  |  |  | 0 | Not prioritized
No capability program for BSPO handling population-related programs | To increase cability of BSPO to handle population related concerns | PopDev Program | Capability building | Conducted atleast 1 Capability Building Training | >1 BSPO Performance evaluation & target setting conducted > 1 BSPO updating course conducted | 20000 | 90000 |  |  | 90000 | 70,000.00 Incentive for BSPO
High incidence of malnourised children(0-5yo) | To decrease incidence of malnourished children by 12% | Nutrition Program | Supplemental Feeding program through counterparting with PHO and LGU | Conducted feeding program in Day Cares and Elementary Schools | > Distribution of vegetables seeds > Supplemental Feeding is given to malnourished and elementary pupil >Nutrition Month Celebration | 100000 | 100000 |  |  | 100000
Low percentage of immunization and lack of awareness on importance on usage of iodized salt | To provide proper immunization | Institutionalizatin of Health & Nutrition Program (immunization, salt iodization, etc.) | Immunization, Salt Iodization, etc. | Conducted immunization every Wednesday and Salt Iodization atleast once every year | > National Immunization Program is implemented/conducted every Wednesday > Intensified advocacies on the importance of Iodize Salt | 50000 | 50000 |  |  | 50000
Rampant simulation of Birth of illegitimate Children | To eliminate simulation of Birth of child | Birth Registry | 1.Distribution of IEC Materials -Information Dissemination on legal adoption - | 1.Distributed IEC Materials to 14 barangays | > 3 barangays were conducted of mobile registration | 5000 | 5000 |  |  | 5000
Not accredited Day Care Workers & Day Care Centers | To conduct seminar on DCW Assessment tools and new manual | Day Care Worker Program | Training on Assessment tools and new Manual for Day Care Workers | 1. Conducted training on assessment tools to 21 Child Development Workers (CDW) | > Monthly Meeting and updating of Programs | 50000 | 30000 |  |  | 30000 | To be implemented this year
8 Day Care Centers are not on specified standard as per DSWD Guidelines | To provide conducive learning environment for Children | Improvement of Standard Day Care Centers | Improvement of Day Care Centers to meet specified standard | atleast 1 day care center improved | 3 Day Care Centers established | 100000 |  |  | 20000 | 20000 | 80,000.00 2 DCC funded by KALAHI, 1 by MAGDALO Partylist
Children needs venue to participate and be developed | To develop children's psychosocial aspects of life | Day Care Services Program; National Children's Month Celebration | Municipal District Congress for Day Care | Conducted Municipal District Congress for Day Care | > Conducted Municipal District congress for Day Care | 50000 | 50000 |  |  | 50000
(4): Search for Day Care; (5): Conducted Search for Day Care; (6): > Conducted search for Day Care in January; (7): 10000 | 5000 |  |  | 5000
(4): Recognition Program; (5): Conducted Recognition Program; (6): Conducted recognition program in March; (7): 10000 | 10000 |  |  | 10000
(4): Little Local Officials Mock Session with Sangguinan; (5): Conducted Little Local Officials and Celebrated National Children's Month; (6): 30 Pupils served as Little Local Official for 3 days; (7): 20000 | 20000 |  |  | 20000
Inadequacy of Maternal and Post Natal Care Services | To provide adequate maternal and post natal care to pregnant women | Maternal and Post Natal Care Program | Provision of Maternal and Post Natal Care | Conducted maternal and Post Natal Care Service | > Maternal Services were provided to 225 pregnant women & post partum services to 185 post partum women | 50000 | 50000 |  |  | 50000
14 barangays have temporay evacuation centers only (RA 10121-Phil. Risk Reduction and Management Act) | To provide evacuation centers to survivors of Disaster/s | Municipal Risk Reduction and Management Program | Construction/Rehabilitation of Evacuation Centers | Constructed/Rehabilitated atleast 2 evacuation center | > Rehabilitation of 4 identified schools as evacuation center | 150000 |  |  | 143021 | 143021
No Venue for Learnings and Playgrounds for childrens | To provide avenue for learning and play area for childrens | Learning Center and Children's Play Area | Provision of Children's Payground, library, etc | Establishment of Playground | > Maintenance Municipal Plaza/Football ground/Children's Playground | 200000 | 251823.5 |  | 20670 | 272493.5 | 72,493.50 Hired personnel for maintenance of plaza and playground
(1): Sub-Total A; (7): 2495000 | 1219262.5 | 0 | 675455 | 1894717.5
ORGANIZATIONAL FOCUSED
More than 40% of LGU employees have not attended Gender Sensitivity Training | To increase knoweldge of LGU Officials/employees on GAD | Human Resource Dev't. Program | Conduct of GAD Trainings/Seminars | Conducted atleast 1 GST for employees | > GAD workshop on LGU Plan and Budget last March 2017 | 100000 | 159680 |  |  | 159680 | 59,000 More participants
Lack of sex disaggregated data(eg. On issuance of permits and licenses, agri data, etc.) | To maintain sex disaggregated data | Database Management | Preparation of GAD database | GAD Database |  | 20000 | 20000 |  |  | 20000
Absence of Pre-Marriage Counselling Room | To provide PMC room conducive for couples to protect confidentiality | FP Program | 1.Construction of PMC Room | 1 marriage counselling room constructed |  | 500000 |  |  |  | 0 | To be prioritized next year
Sports Program for All | To support sports activities | Sports Development Program | Implementation of Sports Development Program | Conducted atleast 1 sports activity. | > Conducted summer sports activities for youth > Support to in-school sports activities | 300000 | 457640 |  |  | 457640 | 157,640.00 More sports activities conducted
No Venue for Learnings and Playgrounds for childrens | To provide a venue for learning and play area for childrens | Learning Center and Children's Play Area | Provision of Children's Payground, library, etc | Constructed atleast 1 playground -acquired books for library |  | 200000 |  |  |  | 0 | To be prioritized next year
(1): Sub-Total B; (7): 1120000 | 637320 | 0 | 0 | 637320
ATTRIBUTED PROGRAMS
(1): Title of LGU Program or Project; (6): HGDG PIMME/ PIMME Score; (7): Total Annual Program/ Project Cost or Expenditure |  |  |  | GAD Attributed Program/ Project Cost or Expenditure | Variance or Remarks
(1): (10); (6): (11); (7): (12) |  | MOOE | PS | (13) | (14)
(1): Sub -total C | 0 | 0 | 0
(1): GRAND TOTAL; (7): 3615000 | 1856582.5 | 0 | 675455 | 2532037.5
Prepared by: |  |  | Approved by: |  | Date:
MAE R. GALLAZA |  |  | HON. MARK P. PALABRICA |  | 26/02/2018
Chairperson - TWG-GFPS |  |  | Local Chief Executive |  | DD/MM/YEAR