## Sheet1
FDP Form 6 - Trust Fund Utilization
Consolidated Quarterly Report on Government Projects /Programs/Activities
For the 1st Quarter, CY 2017
Province, City or Municipality : Bingawan, Iloilo
Project/Program/ Activity Name | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Road/Rehab Spot Concreting on Critical Slope Area | Brgy. Bulabog | 1971666.67 | July 2, 2015 | October 9, 2015 | 100% | 1769677.42 |  | Request for Inspection at COA Region
Road/Rehab Spot Concreting on Critical Slope Area | Brgy. Cairohan | 1971666.67 | July 2, 2015 | October 9, 2015 | 100% | 1769677.42 |  | Request for Inspection at COA Region
Road/Rehab Spot Concreting on Critical Slope Area | Brgy. Quinangyana | 1971666.67 | July 2, 2015 | October 9, 2015 | 100% | 1769677.42 |  | Request for Inspection at COA Region
Road/Rehab Spot Concreting on Critical Slope Area | Brgy. Poblacion | 1971666.67 | July 2, 2015 | October 9, 2015 | 100% | 1769677.42 |  | Request for Inspection at COA Region
Road/Rehab Spot Concreting on Critical Slope Area | Brgy. Malitbog Ilawod | 1971666.67 | July 2, 2015 | October 9, 2015 | 100% | 1672313.55 |  | Request for Inspection at COA Region
Road/Rehab Spot Concreting on Critical Slope Area | Brgy. Guinhulacan | 1971666.67 | July 2, 2015 | October 9, 2015 | 100% | 1641502.72 |  | Request for Inspection at COA Region
Design and Build for Rehab and Extension of Bingawan Level lll Water System | Brgy. Poblacion | 8000000 | Oct. 9, 2015 | April 29, 2016 | 100% | 7998000
Conreting/Rehab of Junction Agba-o - Tapacon - Inamyungan - Guinhulacan FMR with Bridge | Brgy. Agba-o, BrgyTapacon, Brgy. Inamyungan, Brgy. Guinhulacan | 68099839.58 | March, 2015 | 240 CD | 61.31% | 16963785.51 |  | On-going
Construction/Expansion of Water System Level II | Sitio Maldespina, Brgy. Poblaacion | 1350000 | Nov. 3, 2014 | 2015-03-03 | 100% | 1214953.53 |  | Request for Inspection at COA Region
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
LEIZEL M. NERI, CPA |  |  |  | MARK P. PALABRICA
Municipal Accountant |  |  |  | Municipal Mayor