## Mayor
20% IRA UTILIZATION for 2014
OBJECT OF EXPENDITURES |  |  | Total Appropriations |  | Disbursement |  | Available Appro.
|  |  | 2014 |  |  |  | as Nov. 20,2014
Social Development
1. Rehabilitation of Cultural/Historical Sites |  |  | 400000 | 400000 | 400000 |  | 0
2. Construction/Rehab. of Evacuation Centers |  |  | 300000 | 300000 | 163144.5 | 163144.5 | 136855.5
3. Senior Citizens & Persons with Disability Program |  |  | 50000 | 50000 | 50000 | 50000 | 0
4. Program for the Protection of Children |  |  | 25000 | 25000 | 25000 |  | 0
5. Installation of Street Lighting |  |  | 35000 | 35000 | 33226.5 |  | 1773.5
6. Water & Sanitation Projects |  |  | 100000 | 100000 | 0 |  | 100000
7. Purchase of Lot for RHU-Birthing Facility |  |  | 254733.34 | 254733.34 | 254733.33 | 254733.33 | 0.01
8. Mun.Counterpart for Prog./ Projects & Activities |  |  | 500000 | 500000 | 41250 | 41250 | 458750
9. Maternal, Infant, Child Health Care, Services Prog. |  |  | 10000 | 10000 | 0 |  | 10000
10. Daycare Services, Population Services Program |  |  | 10000 | 10000 | 9000 | 9000 | 1000
11. NHIP |  |  | 491000 | 491000 | 338358 |  | 152642
12. Purchase of Medicine & Medical Supplies |  |  | 100000 | 100000 | 74544 | 74544 | 25456
13. Youth Scholarship Program |  |  | 50000 | 50000 | 40000 |  | 10000
14. Adolecent Youth & Sports Development Program |  |  | 340000 | 200000 | 319392.05 | 319392.05 | 20607.95
15. Special Program for Employment of Student |  |  | 120000 | 120000 | 102480 | 102480 | 17520
16. Capacity Bldgs /Training/Seminar/Honorarium |  |  | 88506.66 | 88506.66 | 10000 | 10000 | 78506.66
in Gad related Prog, Projects & activities
ECONOMIC SERVICES
1. Payment of LBP Loan of Public Market |  |  | 2400000 | 2400000 | 2320853.81 |  | 79146.19
2. Payment of Loan of Dumptruck |  |  | 220000 | 220000 | 0 |  | 220000
3. Payment of Loan for the Purchase of Road Grader |  |  | 1000000 | 1000000 | 400000 |  | 600000
4. Improvement of FMR/Cost./rehab of Drainage System |  |  | 600000 | 600000 | 509328.94 |  | 90671.06
5. Purchase of Post Harvest Facilities |  |  | 100000 | 100000 | 81868 | 81868 | 18132
6. Capital Expenditures to the Implementation of Live- |  |  | 100000 | 100000 | 100000 |  | 0
lihood Projects
ENVIRONMENTAL MANAGEMENT
1. Garbage Disposal system/Waste Segregation |  |  | 184800 |  | 131096.6 | 131096.6 | 53703.4
2. Reforestation/Urban Greening Project |  |  | 221760 |  | 134177.15 | 134177.15 | 87582.85
3. Matahum Kag Matinlo |  |  | 200000 |  | 129400.58 | 129400.58 | 70599.42
4. Improvement of Eco-Park |  |  | 443520 |  | 292504.5 | 292504.5 | 151015.5
5. PLanting of Seedling |  |  | 147840 |  | 105508.09 | 105508.09 | 42331.91
6. DA Nursery |  |  | 147840 |  | 86908.88 | 86908.88 | 60931.12
TOTAL |  |  | 8640000 |  | 6152774.93 |  | 2487225.07
Realigned
| FROM |  | TO |  |  |  | AMOUNT
Payment of loan for the purchase |  |  | Rehabilitation of Cultural /
of Road Grader |  |  | & Historical Sites |  |  |  | P 400,000.00
Youth Scholarship Progran |  |  | Sports Development Program |  |  |  | 40000
Capital Expenditures to the implementation
of livelihood Projects |  |  | Sports Development Program |  |  |  | 100000
LDRRMF UTILIZATION FOR , 2014
OBJECT OF EXPENDITURES |  |  | Total Appro. |  | Disbursement |  | Available Appro.
as of Dec. 4 2014
Formulation of CLUP/CDP/LDIP/AIP |  |  | 20000 | 20000 | 15100 |  | 4900
MDRRMC and Bingawan Emercency Responders (BIER)
| Capacity building, contingency planning |  | 60000 | 60000 | 44584.75 | 44584.75 | 15415.25
Conduct training on WASAR for Bingawan Emergency
| Responders (BIER) |  | 60000 | 60000 | 59900 |  | 100
Procurement of office supplies and materials for ope-
| ration center |  | 20000 | 20000 | 12425 |  | 7575
Procurement of recue set equipment |  |  | 60000 | 60000 | 39815 | 39815 | 20185
Repair and Maintenance of generator set |  |  | 23000 | 23000 | 22198.6 | 22198.6 | 801.4
Rehabilitation of Drainage System |  |  | 110880 | 110880 | 90825 | 90825 | 20055
De-clogging of canals |  |  | 73920 | 73920 | 17947.6 | 17947.6 | 55972.4
Improvement of canals |  |  | 73920 | 73920 | 0 |  | 73920
Ins. Of Municipal Buildings, Public Structure, Dumptruck,
Ambulance, Pick-up, van, etc. |  |  | 350000 | 350000 | 5658.42 |  | 344341.58
Rehabilitation of infrastructure projects |  |  | 200000 | 200000 | 52800 | 52800 | 147200
Maint. and repair of other public structure and equipment |  |  | 488280 | 488280 | 395157.86 | 395157.86 | 93122.14
|  | Sub Total | 1540000 |  | 756412.23 |  | 783587.77
Quick reaponse fund 30% (660,000.00) |  |  | 660000 |  | 0 |  | 660000
GRAND TOTAL |  |  | 2200000 |  | 756412.23 |  | 1443587.77
LDRRMF UTILIZATION FOR , 2014
OBJECT OF EXPENDITURES |  |  | Total Appro. |  | Disbursement |  | Available Appro.
as of Dec. 4 2014
Formulation of CLUP/CDP/LDIP/AIP |  |  | 20000 | 20000 | 15100 |  | 4900
MDRRMC and Bingawan Emercency Responders (BIER)
| Capacity building, contingency planning |  | 60000 | 60000 | 44584.75 | 44584.75 | 15415.25
Conduct training on WASAR for Bingawan Emergency
| Responders (BIER) |  | 60000 | 60000 | 59900 |  | 100
Procurement of office supplies and materials for ope-
| ration center |  | 20000 | 20000 | 12425 |  | 7575
Procurement of recue set equipment |  |  | 60000 | 60000 | 39815 | 39815 | 20185
Repair and Maintenance of generator set |  |  | 23000 | 23000 | 22198.6 | 22198.6 | 801.4
Rehabilitation of Drainage System |  |  | 110880 | 110880 | 90825 | 90825 | 20055
De-clogging of canals |  |  | 73920 | 73920 | 17947.6 | 17947.6 | 55972.4
Improvement of canals |  |  | 73920 | 73920 | 0 |  | 73920
Ins. Of Municipal Buildings, Public Structure, Dumptruck,
Ambulance, Pick-up, van, etc. |  |  | 350000 | 350000 | 5658.42 |  | 344341.58
Rehabilitation of infrastructure projects |  |  | 200000 | 200000 | 52800 | 52800 | 147200
Maint. and repair of other public structure and equipment |  |  | 488280 | 488280 | 395157.86 | 395157.86 | 93122.14
|  | Sub Total | 1540000 |  | 756412.23 |  | 783587.77
Quick reaponse fund 30% (660,000.00) |  |  | 660000 |  | 0 |  | 660000
GRAND TOTAL |  |  | 2200000 |  | 756412.23 |  | 1443587.77
SPECIAL EDUCATION FUND FOR 1ST. QUARTER MARCH 31,2013
OBJECT OF EXPENDITURES |  |  | Total Appropriations |  | Disbursement |  | Available Appro.
|  |  | 2013 |  |  |  | 2013
1. Sports and Related Activities |  |  | 150000 |  |  |  | 150000
2. Supplies and Materials |  |  | 50000 |  |  |  | 50000
3. Electrification |  |  | 85000 |  | 18408.93 |  | 66591.07
4. Nutrition & Related Activities |  |  | 5000 |  |  |  | 5000
5. Alternative Learning System |  |  | 20000 |  |  |  | 20000
6. Scouting and Related Activities |  |  | 70000 |  | 3000 |  | 67000
7. Quiz Bee & Other related activities |  |  | 40000 |  | 5000 |  | 35000
8. Repair & Maint. of office Equipment |  |  | 10000 |  |  |  | 10000
9. Repair/rehab/Improvement of School Building
and Facilities |  |  | 70000 |  |  |  | 70000
TOTAL |  |  | 500000 |  | 26408.93 |  | 473591.07
Prepared By:
JEMAIMA B. BILLONES
Municipal Budget Officer

## Sheet2
4
5

## Sheet3
LDRRMF UTILIZATION FOR 1ST. QUARTER ENDING MARCH 31, 2014
OBJECT OF EXPENDITURES |  |  | Total Appro. |  | Disbursement |  | Available Appro.
|  |  | fot 1st. Qtr. 2014 |  |  |  | as of March 27, 2014
Formulation of CLUP/CDP/LDIP/AIP |  |  | 20000 |  | 3600 |  | 16400
MDRRMC and Bingawan Emercency Responders (BIER)
| Capacity building, contingency planning |  | 15000 |  | 0 |  | 15000
Conduct training on WASAR for Bingawan Emergency
| Responders (BIER) |  | 15000 |  | 0 |  | 15000
Procurement of office supplies and materials for ope-
| ration center |  | 5000 |  | 0 |  | 5000
Procurement of recue set equipment |  |  | 15000 |  | 0 |  | 15000
Repair and Maintenance of generator set |  |  | 5750 |  | 0 |  | 5750
Ins. Of Mun. Buildings, Pub. Structure, dumptruck,
| Ambulance, Pick-up, van, etc. |  | 87500 |  | 0 |  | 87500
Rehabilitation of Drainage system |  |  | 27720 |  | 15680 |  | 12040
De-clogging of canals |  |  | 18480 |  | 4948 |  | 13532
Improvement of canals |  |  | 18480 |  |  |  | 18480
Rehabilitation of infratructure projects |  |  | 50000 |  | 52800 |  | -2800
Maint. and repair of other public structure & equipment |  |  | 122070 |  | 0 |  | 122070
|  | Sub Total | 400000 | 400000 | 77028 | 77028 | 322972 | 322972
Quick reaponse fund 30% (660,000.00) |  |  | 165000 |  | 0 |  | 165000
GRAND TOTAL |  |  | 565000 |  | 77028 |  | 487972

## Ist. Qtr.
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE QUARTER, CY ________ | 4th | QUARTER, CY 2013
Municipality : Bingawan
Program or Projects |  |  |  |  | Date | Target | Project Status |  | No. of
|  |  | Location | Total Cost | Started | Completion | % of | Total Cost | Extensions,
[6 empty] | Date | completion | Incurred to | if any | Remarks
Social Development
1. Rehabilitation of Cultural/historical sites |  |  | Bingawan, Iloilo | 400000 | Jan. 2013 | Dec. 2013 | 100% | 400000 |  | Completed
2. Cons./rehab of evacuation centers |  |  | " | 400000 | Jan. 2013 | Dec. 2013 | 61.31% | 245250 |  | P200,000.00 realigned to KALAHI-CIDDSS per MDC
reso. No. 2-2013 & per SB reso.# 03-2013
3. Senior Citizens & Persons w/ disability Prog. |  |  | " | 50000 | Jan. 2013 | Dec. 2013 | 30% | 15000 |  | Continuing
4. Program for the Protection of children |  |  |  | 25000 | Jan. 2013 | Dec. 2013 | 0 | 0 |  | Continuing
5. Installation of street lighting |  |  | " | 34160.6 | Jan. 2013 | Dec. 2013 | 91.51% | 31261.3 |  | Completed
6. Water and Sanitation Project |  |  | " | 100000 | Jan. 2013 | Dec. 2013 | 99% | 99960 |  | Completed
7. Purchase of lot for RHU-Birthing Facility |  |  | " | 254733.34 | Jan. 2013 | Dec. 2013 | 99.21% | 252733.34 |  | Completed
8. Maternal, Infant, Child Health Care Program |  |  | " | 10000 | Jan. 2013 | Dec. 2013 | 0 | 0 |  | Continuing
9. Day Care Services, Population, Service Program |  |  | " | 10000 | Jan. 2013 | Dec. 2013 | 100% | 10000 |  | Completed
10. NHIP Program |  |  | " | 661500 | Jan. 2013 | Dec. 2013 | 75.58% | 500000 |  | Continuing
11. Medicine & Medical Supplies |  |  | " | 100000 | Jan. 2013 | Dec. 2013 | 99% | 99983 |  | Completed
12. Youth Scholarship Program |  |  | " | 50000 | Jan. 2013 | Dec. 2013 | 0 | 0 |  | Continuing
13. Adolecent Youth & Sports Development Program |  |  | " | 250000 | Jan. 2013 | Dec. 2013 | 100% | 250000 |  | P 100,000.00 realigned to KALAHI-CIDDSS per MDC
reso. No. 2-2013 & per SB reso.# 03-2013
14. Special Program for the employment of Student |  |  | " | 120000 | Jan. 2013 | Dec. 2013 | 46% | 56160 |  | Continuing
15. Enhancement/capacity bldg/other GAD activities |  |  | " | 50000 | Jan. 2013 | Dec. 2013 | 98% | 49000 |  | Completed
We hereby certify that we have reviewed the contents and hereby attest
to the veracity and correctness of the data or information contained in
this documents.
JEMAIMA B. BILLONES | [6 empty] | MATT P. PALABRICA,Ph. D.
Municipal Budget Officer | [6 empty] | Municipal Mayor
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE QUARTER, CY ________ | 4th | QUARTER, CY 2013
Municipality : Bingawan
Program or Projects |  |  |  |  | Date | Target | Project Status |  | No. of
|  |  | Location | Total Cost | Started | Completion | % of | Total Cost | Extensions,
[6 empty] | Date | completion | Incurred to | if any | Remarks
ECONOMIC SERVICES
1. Payment of Loan to LBP of Public Market |  |  | Bingawan, Iloilo | 1845266.66 | Jan. 2013 | Dec. 2013 | 100% | 1845266.66 |  | Completed
2. Payment of Loan to LBP (dumptruck) |  |  | " | 250000 | Jan. 2013 | Dec. 2013 | 100% | 250000 |  | Completed
3. Improvement of FMR /rehab of drainage System |  |  | " | 1500000 | Jan. 2013 | Dec. 2013 | 99% | 1499903.14 |  | Completed
4. Improvement /maint. of Public bldgs. ,Parks & Plaza |  |  | " | 383360 | Jan. 2013 | Dec. 2013 | 97.93% | 375432.1 |  | Completed
We hereby certify that we have reviewed the contents and hereby attest
to the veracity and correctness of the data or information contained in
this documents.
JEMAIMA B. BILLONES | [6 empty] | MATT P. PALABRICA, Ph. D.
Municipal Budget Officer | [6 empty] | Municipal Mayor
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE QUARTER, CY ________ | 4th | QUARTER, CY 2013
Municipality : Bingawan
Program or Projects |  |  |  |  | Date | Target | Project Status |  | No. of
|  |  | Location | Total Cost | Started | Completion | % of | Total Cost | Extensions,
[6 empty] | Date | completion | Incurred to | if any | Remarks
ENVIRONMENTAL MANAGEMENT
1. Garbage disposal System/Waste Segragation |  |  | Bingawan, Iloilo | 184800 | Jan. 2013 | Dec. 2013 | 99.56% | 183993 |  | Completed
2. Reforestation/Urban Greening Project |  |  | " | 283360 | Jan. 2013 | Dec. 2013 | 99.96% | 283260 |  | Completed
3. Improvement of Eco- Park |  |  | " | 333360 | Jan. 2013 | Dec. 2013 | 99.49% | 331685 |  | Completed
4. Matahum kag Matinlo Contest |  |  | " | 200000 | Jan. 2013 | Dec. 2013 | 99.47% | 198948.32 |  | Completed
We hereby certify that we have reviewed the contents and hereby attest
to the veracity and correctness of the data or information contained in
this documents.
JEMAIMA B. BILLONES | [6 empty] | MATT P. PALABRICA Ph. D.
Municipal Budget Officer | [6 empty] | Municipal Mayor
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE | 1st. | QUARTER, CY 2014
Municipality : Bingawan
Program or Projects |  |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of
[7 empty] | % of completion | Total Cost Incurred to date | Extensions, if any | Remarks
Social Development
1. Rehabilitation of Cultural/Historical Sites |  |  | Bingawan, Iloilo | 400000 | Jan. 2013 | Dec. 2013 | 23.93% | 95710
2. Construction/Rehab. of Evacuation Centers |  |  | " | 300000 | Jan. 2013 | Dec. 2013 | 19.3% | 57900
3. Senior Citizens & Persons with Disability Program |  |  | " | 50000 | Jan. 2013 | Dec. 2013 | 0% | 0
4. Program for the Protection of Children |  |  |  | 25000 | Jan. 2013 | Dec. 2013 | 0% | 0
5. Installation of Street Lighting |  |  | " | 35000 | Jan. 2013 | Dec. 2013 | 0% | 0
6. Water & Sanitation Projects |  |  | " | 100000 | Jan. 2013 | Dec. 2013 | 0% | 0
7. Purchase of Lot for RHU-Birthing Facility |  |  | " | 254733.34 | Jan. 2013 | Dec. 2013 | 100% | 254733.34
8. Mun.Counterpart for Prog./ Projects & Activities |  |  | " | 500000 | Jan. 2013 | Dec. 2013 | 8.25% | 41250
9. Maternal, Infant, Child Health Care, Services Prog. |  |  | " | 10000 | Jan. 2013 | Dec. 2013 | 0% | 0
10. Daycare Services, Population Services Program |  |  | " | 10000 | Jan. 2013 | Dec. 2013 | 50% | 5000
11. NHIP |  |  | " | 491000 | Jan. 2013 | Dec. 2013 | 0% | 0
12. Purchase of Medicine & Medical Supplies |  |  | " | 100000 | Jan. 2013 | Dec. 2013 | 25% | 25000
13. Youth Scholarship Program |  |  | " | 50000 | Jan. 2013 | Dec. 2013 | 0% | 0
14. Adolecent Youth & Sports Development Program |  |  | " | 200000 | Jan. 2013 | Dec. 2013 | 19.78% | 39557.05
15. Special Program for Employment of Student |  |  | " | 120000 | Jan. 2013 | Dec. 2013 | 10% | 12000
16. Capacity Bldgs /Training/Seminar/Honorarium in Gad related Prog, Projects & activities |  |  | " | 88506.66 | Jan. 2013 | Dec. 2013 | 0% | 0
We hereby certify that we have reviewed the contents and hereby attest
to the veracity and correctness of the data or information contained in
this documents.
JEMAIMA B. BILLONES | [6 empty] | MATT P. PALABRICA,Ph. D.
Municipal Budget Officer | [6 empty] | Municipal Mayor
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE | 1st. | QUARTER, CY 2014
Municipality : Bingawan
Program or Projects |  |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of
[7 empty] | % of completion | Total Cost Incurred to date | Extensions, if any | Remarks
[6 empty] | Date | completion | Incurred to | if any | Remarks
ECONOMIC SERVICES
1. Payment of LBP Loan of Public Market |  |  | Bingawan, Iloilo | 2400000 | Jan. 2013 | Dec. 2013 | 0% | 0
2. Payment of Loan of Dumotruck |  |  | " | 220000 | Jan. 2013 | Dec. 2013 | 0% | 0
3. Payment of Loan for the Purchase of Road Grader |  |  |  | 1000000 | Jan. 2013 | Dec. 2013 | 0% | 0
4. Improvement of FMR/Cost./rehab of Drainage System |  |  | " | 600000 | Jan. 2013 | Dec. 2013 | 21.86% | 131184
5. Purchase of Post Harvest Facilities |  |  | " | 100000 | Jan. 2013 | Dec. 2013 | 49.79% | 49788
6. Capital Expenditures to the Implementation of Live- |  |  | " | 100000 | Jan. 2013 | Dec. 2013 | 0% | 0
lihood Projects
0
We hereby certify that we have reviewed the contents and hereby attest
to the veracity and correctness of the data or information contained in
this documents.
JEMAIMA B. BILLONES | [6 empty] | MATT P. PALABRICA,Ph. D.
Municipal Budget Officer | [6 empty] | Municipal Mayor
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE | 1st. | QUARTER, CY 2014
Municipality : Bingawan
Program or Projects |  |  |  |  | Date | Target | Project Status |  | No. of
|  |  | Location | Total Cost | Started | Completion | % of | Total Cost | Extensions,
[6 empty] | Date | completion | Incurred to | if any | Remarks
ENVIRONMENTAL MANAGEMENT
1. Garbage Disposal system/Waste Segregation |  |  | Bingawan, Iloilo | 184800 | Jan. 2013 | Dec. 2013 | 17.64% | 32608
2. Reforestation/Urban Greening Project |  |  | " | 221760 | Jan. 2013 | Dec. 2013 | 18.65% | 41370
3. Matahum Kag Matinlo |  |  |  | 200000 | Jan. 2013 | Dec. 2013 | 11.74% | 23489.23
4. Improvement of Eco-Park |  |  | " | 443520 | Jan. 2013 | Dec. 2013 | 18.94% | 84021.1
5. Palnting of Seedling |  |  | " | 147840 | Jan. 2013 | Dec. 2013 | 19% | 28280
6. DA Nursery |  |  | " | 147840 | Jan. 2013 | Dec. 2013 | 15.58% | 23044.4
0
We hereby certify that we have reviewed the contents and hereby attest
to the veracity and correctness of the data or information contained in
this documents.
JEMAIMA B. BILLONES | [6 empty] | MATT P. PALABRICA,Ph. D.
Municipal Budget Officer | [6 empty] | Municipal Mayor

## 20% Utilization
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE | 2nd | QUARTER, CY 2017
Municipality : Bingawan
Program or Projects |  |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of
[7 empty] | % of completion | Total Cost Incurred to date | Extensions, if any | Remarks
Social Development
1. Construction /Rehabilitation Evacuation Centers |  |  | Bingawan, Iloilo | 300000 | Jan. 2017 | Dec. 2017 | 0% | 0
2. Water & Sanitation Program |  |  | " | 100000 | Jan. 2017 | Dec. 2017 | 0% | 0
3. Installation /Maintenance of Street Lightings/Procurement of |  |  | "
| Generator Set |  |  | 300000 | Jan. 2017 | Dec. 2017 | 9.137% | 27410
4. Construction/Rehabilitation of Facilities such as Multi-purpose
Hall intended to cater to women, senior citizens, minor, displaced
families , Ips, differently -abled persons |  |  | " | 200000 | Jan. 2017 | Dec. 2017 | 0% | 0
5. Purchase of alarm or warning system and calamity -related rescue
operations equipment |  |  | " | 100000 | Jan. 2017 | Dec. 2017 | 0% | 0
6. Health Sevices Program (Purchase of Medical/Dental /Supplies) |  |  | " | 100000 | Jan. 2017 | Dec. 2017 | 0% | 0
7. Municipal Counterpart for the Development of Programs, Projects
and Activities |  |  | " | 2400000 | Jan. 2017 | Dec. 2017 | 19.75% | 473952.5
8. Establishment /Improvement and maintenance of the standard
Day Care Centers |  |  | " | 100000 | Jan. 2017 | Dec. 2017 | 0% | 0
9. Institutionalization of Health and Nutrition Program (Immunization,
salt iodization/feeding programs, micronutrients supplemental |  |  | " | 50000 | Jan. 2017 | Dec. 2017 | 0% | 0
10. Provision of maternal and post natal care |  |  | " | 50000 |  |  | 0% | 0
11. Construction and maintenance of community infrastructure like
children's playground , library, youth centers, etc. |  |  | " | 100000 |  |  | 0% | 0
12. Strngthening the family through parental care and guidance, family
week celebration and parent education |  |  | " | 20000 |  |  | 0% | 0
13. Provision of Potable Water System |  |  | " | 100000 |  |  | 0% | 0
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE | 2nd | QUARTER, CY 2017
Municipality : Bingawan
Program or Projects |  |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of
[7 empty] | % of completion | Total Cost Incurred to date | Extensions, if any | Remarks
14. Provision of services and programs that respond to the special |  |  | Bingawan, Iloilo
needs, interest and concerns of children and offer appropriate
counselling and guidance to these children and their families |  |  | " | 20000 | Jan. 2017 | Dec. 2017 | 0% | 0
GAD PROGRAM
1. Livelihood Program |  |  | " | 200000 | Jan. 2017 | Dec. 2017 | 0% | 0
2. Water System Program |  |  | " | 100000 | Jan. 2017 | Dec. 2017 | 0% | 0
3. Human Resource Development Program |  |  | " | 100000 | Jan. 2017 | Dec. 2017 | 0% | 0
4. Provision of Gender Facilities |  |  | " | 100000 | Jan. 2017 | Dec. 2017 | 0% | 0
5. Family Planning Program |  |  | " | 20000 | Jan. 2017 | Dec. 2017 | 0% | 0
6. Waste Disposal Management Program |  |  | " | 50000 | Jan. 2017 | Dec. 2017 | 0% | 0
7. PWD Program |  |  |  | 20000 | Jan. 2017 | Dec. 2017 | 0% | 0
8. Water Management Program |  |  | " | 20000 | Jan. 2017 | Dec. 2017 | 0% | 0
9. Nutrition Program |  |  | " | 50000 | Jan. 2017 | Dec. 2017 | 0% | 0
10. Women Program |  |  | " | 100000 | Jan. 2017 | Dec. 2017 | 0% | 0
11. Youth Program |  |  | " | 100000 | Jan. 2017 | Dec. 2017 | 0% | 0
12. Senoir Citizens Program and Services |  |  | " | 100000 | Jan. 2017 | Dec. 2017 | 0% | 0
13. WCPD Program |  |  | " | 40000 | Jan. 2017 | Dec. 2017 | 0% | 0
14. Population Development Program |  |  | " | 20000 | Jan. 2017 | Dec. 2017 | 30% | 6000
15. Day Care Workers Program |  |  | " | 50000 | Jan. 2017 | Dec. 2017 | 0% | 0
16. Livelihood Program/Services for Parents/Responsible Parenthood/
ECARP (Every child a Reader) |  |  | " | 20000 | Jan. 2017 | Dec. 2017 | 0% | 0
17. Special Programs for the Employment of Students |  |  | " | 150000 | Jan. 2017 | Dec. 2017 | 84% | 126000
18. Teen Center Program |  |  | " | 100000 | Jan. 2017 | Dec. 2017 | 0% | 0
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE | 2nd | QUARTER, CY 2017
Municipality : Bingawan
Program or Projects |  |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of
[7 empty] | % of completion | Total Cost Incurred to date | Extensions, if any | Remarks
Economic Services
1. Payment of Loan to DBP for the Purchase of Road Grader |  |  | Bingawan, Iloilo | 1181733 | Jan. 2017 | Dec. 2017 | 50.59% | 597897.34
2. Payment of Loan to DBP for Local Counterpart for ARCP II Project |  |  | " | 507138 | Jan. 2017 | Dec. 2017 | 49.84% | 252752
3. Payment of Loan to LBP for the Const./Rehab. Of Public Market |  |  | " | 1166792 | Jan. 2017 | Dec. 2017 | 0% | 0
4. Construction/Improvement ?Rehab of FMR and Drainage System |  |  | " | 600000 | Jan. 2017 | Dec. 2017 | 41.64% | 249825
5.Capital Expenditures for the Implementation of Livelihood Projects |  |  | " | 100000 | Jan. 2017 | Dec. 2017 | 0% | 0
6. Purchase of Pre and Post Harvest Facilities |  |  | " | 100000 | Jan. 2017 | Dec. 2017 | 0% | 0
7. Municipal Counterpart for the G P B P |  |  | " | 806000 | Jan. 2017 | Dec. 2017 | 0% | 0
Environmental Management
1. Ecological Solid Waste Management Program/Agricultural Services |  |  | "
> Garbage Disposal System/Waste Segragation |  |  | " | 229153.5 | Jan. 2017 | Dec. 2017 | 26.6% | 60956.37
> Reforesttation/Urban Greening |  |  | " | 275000 | Jan. 2017 | Dec. 2017 | 40.46% | 111263.5
> Matahum Matinlo Program/ Clean and Green Program |  |  | " | 200000 | Jan. 2017 | Dec. 2017 | 52.06% | 104127
> Construction, Rehabilitation of MRF, Dumpsite, Eco Park , etc. |  |  | " | 229183.5 | Jan. 2017 | Dec. 2017 | 16.65% | 38158.02
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE | 2nd | QUARTER, CY 2017
Municipality : Bingawan
Program or Projects |  |  |  |  | Date | Target | Project Status |  | No. of
|  |  | Location | Total Cost | Started | Completion | % of | Total Cost | Extensions,
[6 empty] | Date | completion | Incurred to | if any | Remarks
> Planting /Caring of Seedling (along Nationa Highway, Landslide
Prone Areas, Eco-Park, etc.) |  |  | " | 275000 | Jan. 2017 | Dec. 2017 | 37.52% | 103175.58
> Improvement/Maintenance of DA Nursery |  |  | " | 275000 | Jan. 2017 | Dec. 2017 | 32.71% | 89959.5
> Improvement/Declogging of Canals |  |  | " | 275000 | Jan. 2017 | Dec. 2017 | 15.45% | 42477.03
2. Purchase of Garbage Truck |  |  | " | 1500000 | Jan. 2017 | Dec. 2017 | 0% | 0
Total | TOTAL |  |  | 13000000 |  |  | 10.44% | 1357795.76
We hereby certify that we have reviewed the contents and hereby attest
to the veracity and correctness of the data or information contained in
this documents.
JEMAIMA B. BILLONES |  |  | ENGR. DAN P. PLAGATA |  |  |  |  | MARK P. PALABRICA
Municipal Budget Officer |  |  | Municipal Planning and Development Officer |  |  |  |  | Municipal Mayor