## Sheet2
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS OR ACTIVITIES
FOR THE 1ST QUARTER, CY 2018
Municipality of Bingawan, Iloilo
Program of Project |  | Location | Total Cost | Date Started | Target of Completion | Project Status |  | No. of Extension, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
DILG-PCF Concrete Paving of Lampeño Street (including slope protection) |  | Brgy. Poblacion | 3000000 | May 26, 2017 |  | 100 | 2422951.13 |  | Completed
Local Roads |  | Brgy. Ngingi-an | 1040000 | October 5, 2024 | January 28, 2018 | 90 | 864292.95 |  | on-going
Local Roads |  | Brgy. Quinar-upan | 1040000 | October 5, 2025 | January 28, 2019 | 90 | 859052.56 |  | on-going
Local Roads |  | Brgy. Tapacon | 1040000 | October 5, 2026 | January 28, 2020 | 90 | 866701.78 |  | on-going
Conreting/Rehab of Junction Agba-o - Tapacon - Inamyungan - Guinhulacan FMR with Bridge |  | Brgy. Agba-o, BrgyTapacon, Brgy. Inamyungan, Brgy. Guinhulacan | 68099839.58 | March 2015 | January 28, 2022 | 100 | 39648553.25 |  | The contractor request for final inspection to COA Region and DAR National
Construction of Farm to Market Road |  | Brgy. Tapacon | 5380986.84 |  |  | 100 | 3286480.03 |  | The contractor request for payment equivalent to 100% accomplishment
Construction/Spot Concreting with Box of Cairoahan-Bulabog FMR |  | Brgy Cairohan-Bulabog |  |  |  | 100 | 7336685.23 |  | The contractor request for payment equivalent to 100% accomplishment
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| LEIZEL M. NERI, CPA |  |  | MARK P. PALABRICA
| Municipal Accountant |  |  | Municipal Mayor