## Sheet1
FDP Form 6 - Trust Fund Utilization
Consolidated Quarterly Report on Government Projects /Programs/Activities
For the 2nd Quarter, CY 2018
Province, City or Municipality : Bingawan, Iloilo
Project/Program/ Activity Name | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks/ Date Completion
[5 empty] | % of Completion | Total Cost Incurred to Date
Local Roads | Brgy. Agba-o, Bingawan, Iloilo | 1040400 | 10/5/2017 | 1/28/2018 | 100% | 842408.26 |  | 2018-02-08
Local Roads | Brgy. Guinhulacan, Bingawan, Iloilo | 1040400 | 10/5/2017 | 1/28/2018 | 100% | 842339.07 |  | 2018-02-08
Local Roads | Brgy. Malitbog Ilawod, Bingawan, Iloilo | 1040400 | 10/5/2017 | 1/28/2018 | 100% | 842388.28 |  | 2018-02-08
Local Roads | Brgy. Cairohan, Bingawan, Iloilo | 1040400 | 10/5/2017 | 1/28/2018 | 100% | 841002.21 |  | 2018-02-08
Local Roads | Brgy. Bulabog, Bingawan, Iloilo | 1040400 | 10/5/2017 | 1/28/2018 | 100% | 887530.91 |  | 2018-02-15
Local Roads | Brgy. Tubod, Bingawan, Iloilo | 1040400 | 10/5/2017 | 1/28/2018 | 100% | 887511.79 |  | 2018-02-15
Local Roads | Brgy. Ngingi-an, Bingawan, Iloilo | 1040400 | 10/5/2017 | 1/28/2018 | 100% | 864692.95 |  | 2018-01-10
Local Roads | Brgy. Quinar-upan, Bingawan, Iloilo | 1040400 | 10/5/2017 | 1/28/2018 | 100% | 859452.56 |  | 2018-01-10
Local Roads | Brgy. Tapacon, Bingawan, Iloilo | 1040400 | 10/5/2017 | 1/28/2018 | 100% | 867101.78 |  | 2018-01-10
Local Roads | Brgy. Alabidhan, Bingawan, Iloilo | 1040400 | 10/5/2017 | 1/28/2018 | 100% | 892087.55
Local Roads | Brgy. Quinangyana, Bingawan, Iloilo | 1040400 | 10/5/2017 | 1/28/2018 | 100% | 846908.01 |  | 2018-03-20
Local Roads | Brgy. Malitbog Ilaya, Bingawan, Iloilo | 1040400 | 10/5/2017 | 1/28/2018 | 100% | 584899.47
Local Roads | Brgy. Poblacion, Bingawan, Iloilo | 1040400 | 10/5/2017 | 1/28/2018 | 100% | 818638.25 |  | 2018-03-20
Concreting/Rehabilitation of Junction Agba-o-Tapacon-Inamyungan-Guinhulacan FMR with Bridge | Brgy Agba-o, Tapacon, Inamyungan and Guinhulacan, Bingawan | 68099839.58 | 2015-03-30 | 2015-11-24 | 100% | 39648553.25 |  | 2018-06-20
Concrete Paving of Lampeno Street (Including Slope Protection) | Brgy. Poblacion, Bingawan, Iloilo | 3000000 | 2017-05-26 | 2017-08-31 | 100% | 2422951.13 |  | 2018-08-31
Construction of BHS | Bgy. Quinangyana,Bingawan Ililo | 2000000 | 2018-03-27 | 2018-06-27 | 50 | 299246.39 |  | on-going
Construction of BHS | Bgy. Ngingi-an,Bingawan Ililo | 1500000 | 2018-03-27 | 2018-06-27 | 50 | 224241.84 |  | on-going
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
LEIZEL M. NERI, CPA |  |  |  | MARK P. PALABRICA
Municipal Accountant |  |  |  | Municipal Mayor