## qtr3_2018
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE | 3rd | QUARTER, CY 2018
Municipality : Bingawan
Program or Projects |  |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of
[7 empty] | % of completion | Total Cost Incurred to date | Extensions, if any | Remarks
Social Development
1. Construction /Rehabilitation Evacuation Centers |  |  | Bingawan, Iloilo | 300000 | Jan. 2018 | Dec. 2018 | 61.02% | 183062
2. Construction /Rehabilitation of Potable Water System |  |  | " | 1300000 | Jan. 2018 | Dec. 2018 | 0% | 0
3. Installation /Maintenance of Street Lighting System |  |  | " | 300000 | Jan. 2018 | Dec. 2018 | 3.057% | 9172
4. Conatruction/Rehabilitation of Multi-purpose Hall |  |  | " | 1563616 | Jan. 2018 | Dec. 2018 | 0% | 0
5. Municipal Counterpart for the Development of Programs,Projects
and Activities |  |  | " | 2500000 | Jan. 2018 | Dec. 2018 | 23.89% | 597362.5
"
Economic Services
1. Payment of Loan to DBP for the Purchaseof Road Grader |  |  | " | 1123239 | Jan. 2018 | Dec. 2018 | 75.49% | 847967.85
2. Payment of Loan to DBP for Local Counterpart for ARCP II Project |  |  |  | 879262 | Jan. 2018 | Dec. 2018 | 69.81% | 613848.33
3. Payment of Loan to DBP for Local Counterpart/Rehab. of Public Market |  |  | " | 1643883 | Jan. 2018 | Dec. 2018 | 0% | 0
4. Construction/Concreting of Municipal Streets, Farm to Market Road |  |  | " | 1000000 | Jan. 2018 | Dec. 2018 | 0% | 0
5. Capital Expenditures for the Implementation of Livelihood Projects |  |  | " | 100000 | Jan. 2018 | Dec. 2018 | 0% | 0
6. Purchase of Pre and Post Harvest Facilities |  |  | " | 100000 | Jan. 2018 | Dec. 2018 | 0% | 0
7. Payment of Loan to MDFO for the purchase of Heavy Equipment and
Dumptrucks |  |  | " | 1000000 | Jan. 2018 | Dec. 2018 | 0% | 0
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE | 3rd | QUARTER, CY 2018
Municipality : Bingawan
Program or Projects |  |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of
[7 empty] | % of completion | Total Cost Incurred to date | Extensions, if any | Remarks
Environmental Management
1. Ecological Solid Waste Management Program/Agricultural
Sevices
* Garbage Disposal System/Waste Segregation |  |  | Bingawan, Iloilo | 200000 | Jan. 2018 | Dec. 2018 | 75.92% | 151840
* Reforestation /Urban Greening |  |  | " | 320000 | Jan. 2018 | Dec. 2018 | 73.22% | 234300
* Matahum kag Matinlo Program/Clean and Green Program |  |  | " | 200000 | Jan. 2018 | Dec. 2018 | 14.42% | 28850
* Construction/Rehabilitation of MRF, Dumpsite, Eco Park, etc. |  |  | " | 240000 | Jan. 2018 | Dec. 2018 | 19.24% | 46185
* Construction of Drainage System/De-clogging of Canals |  |  | " | 400000 | Jan. 2018 | Dec. 2018 | 21.47% | 85880
TOTAL |  |  |  | 13170000 |  |  | 437.6% | 2798467.68
We hereby certify that we have reviewed the contents and hereby attest
to the veracity and correctness of the data or information contained in
this documents.
JEMAIMA B. BILLONES |  |  | ENGR. DAN P. PLAGATA |  |  |  |  | MARK P. PALABRICA
Municipal Budget Officer |  |  | Municipal Planning and Development Officer |  |  |  |  | Municipal Mayor